## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Analyst | 2025-11-14 | Model Bias: The AI Risk Model (US_03) gives disproportionately high-risk scores to applicants from a specific, low-data region, even with stable income. | Sprint 3 | Data Science Team | Logic/Model Bias | Investigated, re-trained with synthetic data. | 2025-11-20 | Closed | Bias issue reduced by 15%; continuous monitoring scheduled.
2 | Dev Lead | 2025-11-14 | The Model Inference API (US_04) fails to handle valid inputs when the income field is sent as a string instead of a float, causing a server crash. | Sprint 3 | Backend Team | Functionality | Implemented strict input type validation in the API wrapper. | 2025-11-16 | Closed | Backend unit tests updated to cover type checking.
3 | Loan Officer | 2025-11-14 | The Internal Dashboard (US_05) displays the AI score but fails to load the corresponding applicant image (KYC ID) due to a CORS policy error. | Sprint 4 | Frontend Team | Integration/API | Updated CORS headers on the image hosting service (S3 bucket). | 2025-11-18 | Closed | Verified on multiple browsers by QA team.
4 | QA Analyst | 2025-11-14 | AML Check Bypass: If the AML third-party service (US_06) returns a 404 Not Found error, the decision logic proceeds to "Approve" instead of defaulting to "Refer to Officer." | Sprint 3 | Backend Team | Compliance/Logic | Added error handling to force "Manual Review" on any AML API failure code. | 2025-11-21 | Closed | Compliance team signed off on the fix.
5 | Data Scientist | 2025-11-14 | The Feature Engineering pipeline (US_02) drops records with missing address data, which is now mandatory, reducing the valid training set size significantly. | Sprint 1 | Data Science Team | Data Quality | Implemented a mean imputation strategy for missing addresses. | 2025-11-17 | Closed | Data flow now captures 98% of all raw records.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others